## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Navyashree R | 2025-09-07 | PySpark fails with UnsupportedClassVersionError | Sprint 1 | Navyashree R | Others | Upgraded Java from 8 to 17; set JAVA_HOME | 2025-09-08 | Closed | Required Java 17 for PySpark 4.0.1
2 | Navyashree R | 2025-09-12 | winutils.exe not found; Hadoop home error | Sprint 1 | Navyashree R | Others | Downloaded winutils.exe + hadoop.dll; set HADOOP_HOME = C:\hadoop | 2025-09-13 | Closed | Followed Apache Hadoop Windows guide
3 | Navyashree R | 2025-09-25 | Hotspot map too dense (1000+ points) | Sprint 2 | Navyashree R | Logical | Increased hotspot threshold to >1000; used 2-decimal spatial binning | 2025-09-26 | Closed | Improved map readability
4 | Navyashree R | 2025-09-28 | All bounding boxes identical in evidence images | Sprint 2 | Navyashree R | Logical | Updated evidence generator to randomize box positions per frame | 2025-09-29 | Closed | Now shows varied vehicle locations
5 | Navyashree R | 2025-10-10 | st.video(height=300) causes TypeError | Sprint 3 | Navyashree R | User Interface | Removed height parameter for Streamlit compatibility | 2025-10-11 | Closed | Works in all Streamlit versions
6 | Navyashree R | 2025-10-12 | IndentationError in dashboard.py | Sprint 3 | Navyashree R | Standards | Standardized to 4-space indentation; enabled whitespace rendering in VS Code | 2025-10-12 | Closed | Prevents future syntax errors
7 | Navyashree R | 2025-10-14 | Dashboard fails if evidence_records.csv missing | Sprint 3 | Navyashree R | Maintainability | Added file existence check + user-friendly warning | 2025-10-14 | Closed | Improves user experience

## Sheet2
Logical
User Interface
Maintainability
Standards
Others